THE PROFIT BLOG

PROJECT PLAN

AI Tools · Personal Finance · Tech · SaaS Reviews

What this is:  This document is your complete master guide to launching an automated, AI-powered blog from zero. It tells you exactly what accounts to create, what to pay, what to configure, and how to automate 95% of the content pipeline using Claude. Your only job: proofread and hit publish.

PART 1 — ACCOUNTS TO CREATE

Create these accounts in the order shown. Items marked CRITICAL must be done in Week 1.

| # | Platform | URL | What It Does | Priority |
| --- | --- | --- | --- | --- |
| 1 | Domain Registrar (Namecheap or Porkbun) | namecheap.com porkbun.com | Buy your blog domain name (~$10/yr) | CRITICAL |
| 2 | Hostinger (Hosting) | hostinger.com | Hosts your WordPress site. Choose Business plan. | CRITICAL |
| 3 | Google Account | accounts.google.com | Needed for Analytics, Search Console, Docs, Sheets, Gmail | CRITICAL |
| 4 | Anthropic Console (Claude API) | console.anthropic.com | Get your Claude API key for full automation via Make.com | CRITICAL |
| 5 | Make.com | make.com | No-code automation that connects Claude API to your entire workflow | CRITICAL |
| 6 | ConvertKit | convertkit.com | Email list and newsletter platform. Free up to 1,000 subscribers. | CRITICAL |
| 7 | Canva | canva.com | Design featured images (1200x630px) for every article. Free tier works. | High |
| 8 | Buffer | buffer.com | Schedule social posts to Twitter/X, LinkedIn, Pinterest, Facebook | High |
| 9 | Ahrefs (or Semrush) | ahrefs.com semrush.com | Keyword research and competitor analysis. Semrush has a free trial. | High |
| 10 | Ezoic | ezoic.com | Display ad platform. Apply at 10,000+ sessions/month (Month 4-6). | Later |
| 11 | Jasper AI Affiliate | jasper.ai/affiliates | Sign up for 30% recurring commission on AI tool sales | Week 2 |
| 12 | Copy.ai Affiliate | copy.ai/affiliates | Sign up for 30% recurring commission | Week 2 |
| 13 | HubSpot Affiliate | hubspot.com/partners/affiliates | $250–$1,000 per sale commission | Week 2 |
| 14 | Semrush Affiliate | semrush.com/affiliates | $200 per sale — one of the highest payouts in SaaS | Week 2 |
| 15 | Amazon Associates | affiliate-program.amazon.com | 1–10% commission on tech gear and accessories | Week 2 |
| 16 | ConvertKit Affiliate | convertkit.com/affiliates | 30% recurring lifetime commission | Week 2 |
| 17 | PartnerStack (Notion) | partnerstack.com | $10–$20 per Notion signup via their affiliate program | Month 2 |
| 18 | Mediavine | mediavine.com | Premium ad network. Apply at 50,000+ sessions/month. | Month 6+ |

Note:  WordPress itself is installed automatically by Hostinger — you do NOT need a separate WordPress.org account. When you sign up for Hostinger, select the WordPress hosting plan and it installs WordPress for you.

PART 2 — PAYMENTS TO MAKE

Your total Week 1 investment is approximately $50–$70. Everything else is optional or paid monthly as revenue grows.

Week 1 (Required to Launch)

| Item | Cost | Where to Pay | Notes |
| --- | --- | --- | --- |
| Domain Name | $10–$15 / yr | Namecheap or Porkbun | Choose a short, brandable .com name |
| Hostinger Business Plan | $3–$6 / mo (billed annually = ~$36–$72) | hostinger.com | Pay 12 months upfront — cheapest rate. Includes free SSL, email, backups. |
| Anthropic API Credits | $20 one-time (add more as needed) | console.anthropic.com → Billing | Covers ~50–80 full articles. Top up when low. ~$0.25–$0.40 per article. |

Month 1–3 (Recommended)

| Item | Cost | Where to Pay | Notes |
| --- | --- | --- | --- |
| Rank Math Pro | $9 / mo | rankmath.com | Critical SEO plugin. Controls meta titles, schema, sitemaps. |
| Canva Pro | $15 / mo | canva.com | Brand kit, background remover, magic resize. Free tier usable at start. |
| ConvertKit | Free to 1,000 subs then $25/mo | convertkit.com | Start free. Upgrade when you hit 1,000 subscribers. |
| Make.com | Free (1,000 ops) then $9/mo | make.com | Free tier covers basic automation. Upgrade for more scenarios. |
| Pretty Links | $7 / mo | prettylinks.com | Cloaks and tracks affiliate links in WordPress. E.g. yourblog.com/go/jasper |
| WP Rocket | $5 / mo | wp-rocket.me | Page speed plugin. Google scores speed — this alone can lift rankings. |

Month 3+ (Growth Phase)

| Item | Cost | Where to Pay | Notes |
| --- | --- | --- | --- |
| Ahrefs Starter | $29 / mo | ahrefs.com | Real keyword data. Can start with free Google Search Console + free Semrush trial. |
| Lasso WP | $29 / mo | getlasso.co | Beautiful affiliate link display boxes. Boosts click-through rates significantly. |
| Claude Pro | $20 / mo | claude.ai | If doing prompts manually (not via API). API is more cost-effective at volume. |

Budget tip:  Total minimum viable launch cost: ~$50–$90 for Year 1 (domain + 12 months hosting + $20 API credits). Everything else is added as revenue grows. You do NOT need Ahrefs, Lasso, or Claude Pro to start.

PART 3 — DATA TO UPLOAD & CONFIGURE

After creating accounts, these are the things you need to set up and upload. Follow this sequence.

3.1  WordPress Setup (Do This First)

Install Kadence theme: Appearance → Themes → Search "Kadence" → Install → Activate. Free version is fine.

Set colour palette: Customizer → Global → Colors. Set Primary: #0D1B2A, Accent: #0A7EA4, Background: #F9FAFB.

Install Rank Math Pro: Plugins → Add New → Upload the .zip from rankmath.com. Activate → run Setup Wizard.

Connect Google Search Console: Rank Math → General Settings → Webmaster Tools → paste verification code.

Install Google Analytics 4: Rank Math → Analytics → connect your Google account. Pulls traffic data into WP.

Install WP Rocket: Plugins → Add New → Upload. Activate. Default settings are fine to start.

Install Pretty Links: Plugins → Add New → Search "Pretty Links" → Install. Create a group called "Affiliates".

Set Permalink structure: Settings → Permalinks → Post name. This gives clean URLs like /best-ai-tools-for-writers.

Disable Comments: Settings → Discussion → uncheck both "Allow comments" boxes. Saves spam headaches.

Create 4 Categories: Posts → Categories. Add: AI Tools, Personal Finance, Tech Reviews, SaaS Reviews.

3.2  Google Sheets Content Calendar

Create a new Google Sheet called "Blog Content Calendar". Add these columns:

Column A: Keyword

Column B: Article Type

Column C: Target Word Count

Column D: Affiliate Products

Column E: Status

Column F: Draft Link

Column G: Publish Date

Column H: Notes

This sheet becomes the trigger for your Make.com automation — every new row auto-generates a draft.

3.3  ConvertKit Setup

Create a Form: Create a simple email opt-in form. Title: "Get weekly AI & finance tips". Use it as a widget.

Add the form to WordPress: Appearance → Widgets → add ConvertKit Form to Sidebar and below every post.

Create a Welcome Sequence: Automations → New Automation. Send 1 welcome email when someone subscribes.

Welcome email content: Claude will write this for you — use Prompt 8 with subject "Welcome to [Blog Name]".

3.4  Buffer Setup

Connect social accounts: Link Twitter/X, LinkedIn, Pinterest, and Facebook page to Buffer.

Set posting schedule: Twitter: 3x/day. LinkedIn: 1x/day. Pinterest: 5x/day. Facebook: 1x/day.

Pinterest Board: Create boards: "AI Tools", "SaaS Reviews", "Personal Finance Tips", "Tech Reviews".

3.5  Save the Master System Prompt

Save this exact text as a file called MASTER_SYSTEM_PROMPT.txt on your computer. Paste it at the start of EVERY new Claude conversation.

You are the senior content writer and SEO strategist for [YOUR BLOG NAME], a high-authority
blog covering AI tools, personal finance, tech, and SaaS reviews. Your content mirrors the
style and depth of NerdWallet, CNET, and HubSpot Blog.

VOICE & TONE:
- Authoritative but conversational. Write like a knowledgeable friend, not a textbook.
- First-person where appropriate ("In my testing..." / "I recommend...")
- Direct, no filler. Every sentence must earn its place.
- Slightly opinionated. Readers want YOUR take, not just facts.

CONTENT RULES:
- Always target ONE primary keyword. Use it in H1, first 100 words, and conclusion.
- Use H2s and H3s generously. Google rewards structured content.
- Include a comparison table in every review/comparison article.
- Add a "Bottom Line" callout box at the end of every article.
- Include a CTA (call-to-action) after the intro and at the article end.
- Minimum 2,000 words. Aim for 2,500–3,500 for most articles.

AFFILIATE & MONETIZATION RULES:
- Naturally mention 2–3 affiliate products per article where relevant.
- Frame affiliate links as recommendations, never as ads.
- Use "[AFFILIATE LINK: ProductName]" as a placeholder. I will add real links.

OUTPUT FORMAT:
- Always output in clean Markdown (##, ###, **bold**, *italic*, tables).
- Ready to paste directly into WordPress without editing.
- End every article with: meta title, meta description, and 5 tags.

PART 4 — 90-DAY LAUNCH PLAN

This is your complete week-by-week action plan. Total daily time: ~2 hours/day.

WEEK 1 — Foundation

Buy domain + sign up for Hostinger Business plan.

Install WordPress. Install Kadence theme. Set brand colours.

Install Rank Math Pro, WP Rocket, Pretty Links, Google Analytics 4.

Connect Google Search Console.

Create Google Account, Make.com account, ConvertKit account.

Sign up for Anthropic Console (console.anthropic.com) and add $20 API credits.

Save MASTER_SYSTEM_PROMPT.txt to your computer.

Create the Google Sheets Content Calendar with columns from Part 3.2.

Write 3 pillar articles using Claude (Prompts 1+2+3). Aim: 3,000+ words each.

Topics: "Best AI Tools 2025", "Best AI Writing Tools", "Claude vs ChatGPT".

Add featured images in Canva (1200x630px, Navy + Teal brand colours).

Publish all 3 articles. Set up email opt-in widget via ConvertKit.

WEEK 2 — Content Engine Starts

Apply to affiliate programs: Jasper AI, Copy.ai, HubSpot, Amazon Associates, ConvertKit.

Write and publish 3 more articles (comparison + how-to mix).

Set up internal links between all 6 articles using Prompt 10.

Add affiliate link placeholders; replace with Pretty Links URLs once approved.

Send your first welcome email via ConvertKit (Claude writes it in 2 min).

Create Pinterest boards. Pin all published articles. Pinterest is high-ROI for finance/tech.

Set up Buffer. Schedule social captions Claude generated with each article.

WEEK 3 — Comparison Articles & SEO

Write 3 "X vs Y" comparison articles — highest converting type.

Start with: Claude vs ChatGPT, Jasper AI vs Copy.ai, HubSpot vs Mailchimp.

Use Prompt 6 (SERP Steal) — find the current #1 for each and beat it.

Run Prompt 10 to build internal link map across all 9 articles.

Check Google Search Console — your first impressions should be showing.

Send your first weekly newsletter via ConvertKit (use Prompt 8).

WEEK 4 — Programmatic SEO

Run Prompt 5 (Programmatic SEO Batch) to generate 10 article outlines.

Template: "Best AI Tools for [Profession]" — writers, lawyers, teachers, etc.

Write and publish 3–5 of these. They rank fast and earn affiliates with minimal effort.

Apply to Ezoic for display ads (requires 10,000 sessions — this builds toward it).

Install Make.com automation (see Part 5) — keyword → draft now runs automatically.

MONTH 2 — Scaling

25 articles live. First affiliate clicks should be happening.

Start weekly email newsletter every Friday (Prompt 8 takes 3 minutes).

Run SERP Steal tactic (Prompt 6) on 3 competitor articles.

Use Prompt 7 to refresh your Month 1 articles with current data.

Check affiliate dashboards weekly — note which products are converting.

Add internal links: every new article should link to 4–6 older articles.

MONTH 3 — First Revenue

50 articles live. Target: first $100–$500 in affiliate income.

Update Month 1 articles with 2025/2026 data using Prompt 7.

Launch your first digital product: a simple prompt pack or template for $9–$19.

Sell via Gumroad (free account) — no coding needed.

Analyse Google Search Console: which articles get impressions but low clicks?

Improve those titles and meta descriptions using Prompt 4.

Apply to Semrush affiliate program ($200/sale — one of the best payouts).

PART 5 — AUTOMATION SETUP

This is the Make.com + Claude API automation that runs your content pipeline on autopilot. Set-up time: ~45 minutes. After that, every keyword you add auto-generates a full draft.

5.1  Get Your Claude API Key

Go to console.anthropic.com and sign in.

Click "API Keys" in the left sidebar.

Click "Create Key". Name it "Blog Automation".

Copy the key immediately — you only see it once. Save it in a password manager.

Click "Plans & Billing" → Add $20 in credits to start.

5.2  Make.com Scenario: Keyword → Draft (Core Automation)

This is the most important automation. When you add a keyword to your Google Sheet, Claude automatically writes the full article and saves it to Google Docs.

Open Make.com→ New Scenario.

Module 1 — TRIGGER:Google Sheets → "Watch Rows". Connect your Google account. Select your Content Calendar sheet. Watch: all rows.

Module 2 — HTTP Request to Claude API:
URL: https://api.anthropic.com/v1/messages
Method: POST
Headers:
  x-api-key: [YOUR API KEY]
  anthropic-version: 2023-06-01
  content-type: application/json

Module 2 — Request Body (paste this exactly):

Module 3 — Google Docs:→ "Create Document"
Name: {{1.keyword}} — DRAFT
Content: {{2.content[].text}}
Folder: create a "Blog Drafts" folder in Google Drive.

Module 4 — Gmail or Slack:→ send yourself a notification: "New draft ready: {{1.keyword}}"

Set schedule:Click the clock icon → run "Immediately" when a row is added.

Test it:Add a test keyword to your sheet. Click Run Once. Check Google Docs for the draft.

Request body to paste into Module 2:

{
  "model": "claude-opus-4-5",
  "max_tokens": 8000,
  "system": "[PASTE YOUR MASTER SYSTEM PROMPT HERE — the full text from Part 3.5]",
  "messages": [{
    "role": "user",
    "content": "Write a complete SEO article for keyword: {{1.keyword}}. Follow all rules in your system prompt."
  }]
}

5.3  Full Automation Table

Build these 6 Make.com scenarios in order. Each takes 10–15 minutes to set up.

| Scenario | Trigger | What Claude Does | Output |
| --- | --- | --- | --- |
| 1. Weekly Keywords | Every Monday 9am | Generates 5 keyword ideas for the week | Adds rows to Google Sheet calendar |
| 2. Article Draft | New row in Google Sheet | Writes full article from keyword | Saves draft to Google Docs folder |
| 3. SEO & Distribution | Draft saved to Docs | Title, meta, social captions, email newsletter | Saves to a "Distribution" folder in Drive |
| 4. Newsletter | Every Friday 8am | Writes weekly email from that week's articles | Sends draft to ConvertKit as a broadcast |
| 5. Social Posts | Draft marked "Published" | Posts captions to Twitter, LinkedIn, Pinterest | Scheduled via Buffer API |
| 6. Monthly Refresh | 1st of each month | Flags articles older than 6 months for update | Creates update queue in Google Sheet |

5.4  Cost of API Usage

| Volume | Articles/Month | API Cost/Month | Time Saved | Revenue Potential |
| --- | --- | --- | --- | --- |
| Starter | 8 articles | ~$3 | 30 hours | $500–$2,000/mo (Month 6+) |
| Growth | 16 articles | ~$6 | 60 hours | $2,000–$6,000/mo (Month 9+) |
| Scale | 30 articles | ~$12 | 112 hours | $6,000–$20,000/mo (Year 2) |
| Full Auto | 60 articles | ~$24 | 220 hours | $15,000–$50,000/mo (Year 2–3) |

PART 6 — ALL 10 PROMPTS (COPY-PASTE READY)

Paste the Master System Prompt first in every new Claude conversation. Then use any prompt below.

MASTER SYSTEM PROMPT

When to use: Paste at the start of EVERY new Claude session. This locks in your voice, rules, and monetization strategy.

See full text in Part 3.5 above. Save as MASTER_SYSTEM_PROMPT.txt on your desktop.

PROMPT 1 — Weekly Keyword Research

When to use: Run every Monday morning. Gets 5 article ideas with keywords, types, and affiliate suggestions.

I need 5 article ideas for this week. My blog covers AI tools, personal finance, tech, and SaaS reviews.
Target readers: professionals aged 25-45 who want to save money and work smarter using technology.

For each idea, give me:
- Primary keyword (long-tail, commercial intent, under 5,000 monthly searches)
- Article type (comparison / best-of listicle / how-to / review)
- Estimated word count
- Top 2 affiliate products to mention
- Why this keyword will rank (low competition angle)

Prioritize keywords where the reader is about to make a purchase decision.
Include at least 2 "X vs Y" comparison keywords this week.

PROMPT 2 — Article Brief Generator

When to use: Run after Prompt 1. Creates a full SEO brief and outline before writing.

Create a full SEO brief for the article: "[KEYWORD FROM MONDAY]"

Include:
- Confirmed primary keyword + 5 LSI keywords to weave in naturally
- Exact H2 and H3 outline (minimum 6 H2s)
- Word count target (based on beating the top 3 Google results)
- Specific affiliate products to recommend (with placement suggestions)
- 3 competitor gaps (what the top results are missing that I should cover)
- Suggested featured image description
- Internal linking opportunities (refer to my other likely topics)

PROMPT 3 — Full Article Draft

When to use: Run immediately after Prompt 2. Produces the complete article in Markdown.

Write the complete article from the brief above.

Requirements:
- Full article in clean Markdown, ready for WordPress
- Start with a compelling 2-paragraph hook (problem + promise of solution)
- Use the H2/H3 structure from the brief exactly
- Include a comparison table if this is a review or comparison piece
- Add a visually distinct "Pro Tip" callout after section 3
- Add [AFFILIATE LINK: ProductName] placeholders (do NOT invent URLs)
- Add a "Bottom Line" box before the conclusion
- End with a strong CTA paragraph
- Final 3 lines: SEO Title | Meta Description | Tags (comma-separated)

Do not add any commentary outside the article. Output ONLY the finished article.

PROMPT 4 — Full Distribution Pack

When to use: Run after every article. Generates SEO metadata, all social captions, email, and internal link suggestions.

Based on the article above, generate the full distribution pack:

1. SEO METADATA
   - SEO title (max 60 chars, primary keyword near front)
   - Meta description (max 155 chars, include keyword + action word)
   - Focus keyword for Rank Math

2. SOCIAL CAPTIONS (one per platform)
   - Twitter/X: punchy, under 240 chars, add relevant hashtags
   - LinkedIn: professional insight angle, 3-4 sentences, no hashtags
   - Pinterest: keyword-rich, 200-250 chars, searchable
   - Facebook: conversational, question hook to drive comments

3. EMAIL NEWSLETTER (for ConvertKit send)
   - Subject line (curiosity-driven, under 50 chars)
   - Preview text (under 90 chars)
   - Newsletter body: 150-word teaser + link placeholder [ARTICLE URL]

4. INTERNAL LINKS
   - 5 anchor text suggestions + the topic they should link to

PROMPT 5 — Programmatic SEO Batch

When to use: Run monthly. Generates 10 article outlines at once to build topical authority fast.

I want to build topical authority fast using programmatic SEO.
Take this template article structure: "Best AI Tools for [PROFESSION]"

Generate complete article OUTLINES (not full articles yet) for these 10 professions:
Writers, Lawyers, Accountants, Real Estate Agents, Teachers, Freelancers,
Developers, HR Managers, Marketers, Small Business Owners.

For each, give me:
- Unique primary keyword (e.g., "best AI tools for lawyers 2025")
- 6 H2 headings tailored to that profession's specific needs
- Top 3 affiliate tools to feature (profession-relevant)
- One unique angle that makes this article different from generic AI lists

Format as a table: Profession | Keyword | H2s | Tools | Angle

PROMPT 6 — SERP Steal (Outrank Competitors)

When to use: Use when you find a #1 article you can beat. Paste the competitor article text.

I want to outrank the current #1 Google result for "[KEYWORD]".

Here is the content from the top-ranking article:
[PASTE THE COMPETITOR ARTICLE TEXT HERE]

Analyze it and tell me:
- What is it missing that readers would want?
- What questions does it not answer?
- What is outdated or could be more specific?
- What affiliate/monetization opportunities did it miss?

Then write a BETTER version of this article that:
- Covers everything it covers PLUS fills every gap you identified
- Is at least 500 words longer
- Has more specific, actionable advice
- Includes a comparison table it lacks
- Has a stronger CTA and affiliate integration

PROMPT 7 — Article Refresh

When to use: Use monthly to update articles older than 6 months. Paste your old article text.

This article was written in [YEAR] and needs a full refresh for 2025/2026.
[PASTE YOUR OLD ARTICLE HERE]

Update it by:
- Replacing any outdated statistics with placeholders: [UPDATE STAT: topic]
- Flagging any tools/products that may have changed: [VERIFY: tool name]
- Adding a new section on how AI has changed this topic
- Updating the intro to reference 2025/2026 context
- Adding 2-3 new H2 sections covering angles not in the original
- Refreshing the comparison table with current pricing/features
- Updating the Bottom Line with a fresh recommendation

Keep my original voice. Do not rewrite sentences that are still accurate.
Output the full updated article in Markdown.

PROMPT 8 — Weekly Newsletter

When to use: Run every Friday. Takes 3 minutes. Paste your 3 article titles and summaries.

Write this week's blog newsletter for [YOUR BLOG NAME].

This week's published articles:
1. [ARTICLE TITLE 1] — [ONE LINE SUMMARY]
2. [ARTICLE TITLE 2] — [ONE LINE SUMMARY]
3. [ARTICLE TITLE 3] — [ONE LINE SUMMARY]

Write a newsletter with:
- Subject line: curiosity + benefit, under 45 characters
- Preview text: teaser that makes them open it, under 85 chars
- Greeting: warm, first-name style ("[First Name],")
- Intro paragraph: 2 sentences, relatable hook
- Article 1 feature: 3 sentences + [LINK 1] CTA
- Article 2 tease: 2 sentences + [LINK 2] CTA
- Article 3 tease: 2 sentences + [LINK 3] CTA
- Deal/tip of the week: 1 relevant affiliate mention
- Sign-off: casual, personal, 2 lines max

Tone: like a smart friend sharing what they found this week. Not corporate.

PROMPT 9 — Full Affiliate Product Review

When to use: Use for any product you want to review. Structured like CNET/NerdWallet.

Write a full affiliate review article for: [PRODUCT NAME]
Primary keyword: "[PRODUCT NAME] review [YEAR]"
Affiliate program: [COMMISSION DETAILS]

Structure it exactly like CNET/NerdWallet review format:
- Headline with verdict: "[Product] Review: [One-Line Verdict]"
- Quick verdict box: Pros (4 bullets) | Cons (3 bullets) | Rating: X/10
- What is [Product]? (100 words, for beginners)
- Who is it for? (3 ideal user types)
- Key features breakdown (one H2 per major feature, specific + opinionated)
- Pricing breakdown table (all tiers, what you get, is it worth it)
- [Product] vs competitors (mini comparison table, 3 alternatives)
- Real-world performance (write as if you tested it personally)
- Bottom Line + final recommendation
- CTA: "[AFFILIATE LINK: ProductName]" with strong action framing

Write at 3,000+ words. Be opinionated. Readers want a verdict, not a feature list.

PROMPT 10 — Internal Link Map

When to use: Run after every 5th article. Builds the link architecture that Google rewards.

Here is a list of all my published articles:
[PASTE YOUR ARTICLE TITLES AND URLS HERE]

For the new article I just wrote about "[NEW KEYWORD]", identify:
- Which 5-8 existing articles should I link TO from the new article
  (with suggested anchor text for each)
- Which 3-5 existing articles should link BACK to the new article
  (with suggested anchor text and the sentence context to insert it)

Then build me a full internal link map showing which pillar articles should
receive the most internal links (these are my "authority hubs").
Format as a table: Article | Links From | Links To | Authority Score (1-10)

PART 7 — PUBLISH WORKFLOW (PER ARTICLE)

This is your 15–20 minute routine for each article. Claude has already done the hard work.

Open draft in Google Docs (auto-saved by Make.com automation).

Read it once — fix any factual errors. Add 1–2 personal sentences (e.g., "In my testing..."). This is what separates your blog from pure AI content.

Open WordPress → Posts → New Post. Paste the Markdown into the content editor (use a Markdown block or the raw editor).

SEO tab (Rank Math) → paste the SEO title, meta description, and focus keyword Claude generated at the end of the article.

Affiliate links → search for [AFFILIATE LINK: X] placeholders. Replace each with your Pretty Links URL (e.g., yourblog.com/go/jasper).

Featured image → open Canva. Use your brand template (1200x630px, Navy/Teal). Add the article headline. Download and upload to WordPress.

Categories & tags → apply from Claude's tag suggestions at the bottom of the article.

Internal links → use Claude's link map (Prompt 10) to add 4–6 internal links to other articles.

Preview on mobile → 60%+ of your readers are on phones. Check it looks right. Adjust font sizes if needed.

Publish or schedule → schedule for 7:00am the following morning for best organic reach.

Social captions → copy from the Distribution Pack (Prompt 4). Paste into Buffer. Schedule for that day.

Newsletter → if it's your send day (Friday), paste Claude's email into ConvertKit. Hit send.

Real numbers:  Total time per article: 24–31 minutes. Claude handles ~15 hours of equivalent manual work per week. At 3 articles/week your total weekly contribution is ~90 minutes of your time.

PART 8 — REVENUE MILESTONES & WHAT TO DO AT EACH STAGE

| Milestone | Timeframe | Revenue Target | Key Action at This Stage |
| --- | --- | --- | --- |
| 10 articles live | Week 2–3 | $0 — building | Apply to Jasper, Copy.ai, Amazon Associates affiliate programs |
| 25 articles live | Month 2 | $0–$100 | Apply to Ezoic ads. Start weekly newsletter. Run SERP Steal on 3 competitors. |
| 50 articles live | Month 3 | $100–$500 | Launch digital product ($9–$19 prompt pack). Update Month 1 articles. |
| 10,000 sessions/mo | Month 4–5 | $300–$800 | Ezoic ads go live (RPM $8–$15). Double affiliate link coverage. |
| 50,000 sessions/mo | Month 6–8 | $800–$3,000 | Apply to Mediavine (RPM $15–$25). Add HubSpot + Semrush affiliates. |
| 100 articles live | Month 6–9 | $2,000–$6,000 | Full automation firing. Consider hiring editor for 1 hour/week. |
| 100,000 sessions/mo | Month 9–12 | $5,000–$15,000 | Apply to AdThrive (RPM $20–$40). Launch blog growth course ($97–$297). |
| Year 2 full stack | Year 2 | $8,000–$25,000/mo | Affiliate + ads + products + email all compounding. Scale content to 5x/week. |

You are the editor. Claude is your entire team.

Keyword in. Proofread article out. Publish. Repeat.